## ArtsFAS
(Draft Micro Grant June 2025)
| Insert applicant logo here [Sertakan logo permohon di sini] | PROPOSED BUDGET & IMPLEMENTATION PLAN [CADANGAN BAJET & PELAN PELAKSANAAN]
Project Title [Tajuk Projek]:
Applicant/ Organisation Name [Nama Pemohon Organisasi] :
Funding Period [Tempoh Dana] :
| Total amount requested [Jumlah yang dipohon]: | 50500
| Proposed Budget [Cadangan Bajet] | Unit | Total Requested Amount [Jumlah yang dimohon] | Implementation Plan
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project Implementation Cost [Kos Pelaksanaan Projek]
1 | For example Output 1: 20 artisans trained in digital marketing for Keringkam |  | 22000
| Activity 1.1 - Hire trainer | 1 | 5000 | bar: Implementation Plan Jan
| Activity 1.2 - Logistics and venue bookings | 1 | 5000 | bar: Implementation Plan Feb
| Activity 1.3 - Recruitment and selection process | 1 | 2000 | bar: Implementation Plan Feb to Implementation Plan Mar
| Activity 1.4 - Training 4 hours x 4 weeks x 3 months x 20 pax | 20 | 10000 | bar: Implementation Plan Apr to Implementation Plan Jun
2 | Output 2: … |  | 0
Activity 2.1 - …
Activity 2.2 - …
Activity 2.3 - …
Activity 2.4 - …
Other Implementation Cost [Lain-lain Kos Pelaksanaan Projek]
Cost related to the project implementation. For example: Administrative costs, staff salaries, Marketing & promotion, transportation cost, travel etc [Kos yang berkaitan dengan pelaksanaan projek. Contoh: Pengurusan projek, kakitangan, tuntutan perjalanan dsbg.]
1 | Project Staff Cost |  | 26000
1.1 | Project Manager (7 Months) | 1 | 21000 | bar: Implementation Plan Jan to Implementation Plan Jul
1.2 | Volunteers (2 Pax, 5 months) | 10 | 5000 | bar: Implementation Plan Apr to Implementation Plan May
2 | Marketing & Promotion |  | 2500
2.1 | Social Media Posting: Instagramme (2 Posts for 5 weeks) | 10 | 1000 | bar: Implementation Plan May to Implementation Plan Jul
2.2 | Radio Interview @ Klasik.FM | 1 | 1500 | bar: Implementation Plan May to Implementation Plan Jun
3
Please add other budget items specific to the nature of the project [Sila nyatakan item bajet yang lain khusus untuk projek]
| Total (RM) [Jumlah] |  | 50500
Note:
Please replace all examples shown in orange with your project’s actual budget and implementation timeline. Do not leave the example text in the template.